## Tabelle1
SR Number | Status | Topic | Effort magnitude | Est. efft ND (developt) | Est. efft WS (total effort) | Feat. Category
16400 | non GUI | Basic/Advanced Mask: only mandatory inputs in basic mask (specification work) | Week
| non GUI | Configure the resource management on the Solaris Arsenal system | Week
| non GUI | Meaningful default values in the reports so that clicking on Search yields an instant result (specification work) | Week
16500 | Done | Authenticated Emails | Week
16723 | Done | Grid lines in the charts | Day
16743 | Done | Get rid of message "combination of input values not allowed" (DB error code 21011, Autodoc & DB work) | Week
14987 | Done | Allow the order of output panels to be configured over metadata (default being: first the charts, then the table) | Day
15022 | Done | JFreeCharts Properties Access => more flexibility in Charts Metadata | Week
| Done | Kill running queries | Week |  | 120 | Legacy
| non GUI | DataXtender Alarming |  |  | 240 | Legacy
15252 | Current | Display/parsing of numeric fields: changes by Katarina as discussed on 17.12.08 and bugfix by Nicolas in OSSDataTypeUtil | Day
16746 | Open | Help texts for report groups and domain package (with link from the report help pages) | Week | 20
14973 | Open | "Last day", "Last month" Favorites buttons | Week | 200 |  | Legacy
16911 | Open | Introduce the ability to change the axes of charts from linear to logarithmic in the GUI (over inputs or pop-up menu) | Week | 100
16747 | Open | Refactoring of OSSUserAdmin Modules (part of Multitenancy Work Package) | Week | 50 |  | Current
14981 | Open | Dashboards | MONTH | 400 | 1400 | Current
16909 | Open | GUI for administration of scheduled reports | Week | 200 | 270 | Current
14972 | Open | Support the back button of the browser using the YUI browser history support (includes migration to the current YUI version) | MONTH | 300 |  | Current
16535 | Open | Sharing & Security of Quick Values | Week | 220 |  | Current
| Open | Multitenancy | MONTH |  | 600 | Current
| Open | User preferences 2.0 (enhancements to the existing User preferences) | Week | 0 |  | Legacy
16686 | Open | Better access to existing reports (Time/User/Network/Service/Device/Other + Filter/Display) | MONTH | 400 | 1200 | Strategic
16555 | Open | Multiple Chart drill-down | MONTH | 250 |  | Strategic
16555 | Open | Dynamic legends in the chart for help or further filtering (remove / drill-down) | MONTH |  |  | Strategic
14985 | Open | Table popup Drilldown | MONTH | 400 |  | Strategic
16745 | Open | Explore BI tools like BIRT/Pentaho/Jasper in order to provide our customers with a complementary offer for advanced users | MONTH | 150 |  | Strategic
16497 | Postponed | Flexible titles for Reports and Charts | Week
16710 | Postponed | Display of legal notices the first time a user logs in (needed for Oracle embedded license) | Day
15012 | Postponed | Better layout of existing Input mask (Line separators) | Day
16579 | Postponed | Help for entering negative values in List Range fields vs normal Value Fields (with popup notice with JS dynamic identification) | Day
16721 | Postponed | Enhance the report output tabbed panel to include a close button | Week